## Sheet1
STATUS REPORT
Project Name |  | Miss & Mrs. BestPrice | Type |  | E-commerce Website |  | Project Team | Cogent
Project Summery |  |  | Key Phases |  |  | Progress | Status | Finish
This project is all about an E-commercrce website.It will provide our client to upload his product on online platform ,and to cutomers,they will get a glimps about the variety,pricing and quality of clothing which is available in the store. |  |  | Analysis |  |  | 100% | Complete | 2020-02-12
|  |  | Development |  |  | 100% | Complete | 2020-05-20
|  |  | Coding |  |  | 100% | Complete | 2020-05-15
|  |  | Testing |  |  | 100% | Complete | 2020-05-25
|  |  | Maintenance |  |  | 100% | Complete | 2020-05-30
Modules Planned |  |  | Modules Completed |  |  |  | Modules Delayed
FOR ADMIN- 1.Admin can login the system. 2.Admin can create categories. 3.Admin can create subcategories. 4.Admin can upload products. 5.Admin can upload product features FOR USERS- 1.User can login the system. 2.User can search for a particular Products. 3.User can order a product. |  |  | All modules have been completed by May 2020. |  |  |  | 1.Payment integration 2.Deployment
Reason for delayed Modules
1.Insufficient knowledge 2.Lack of coordination.
Top 3 risks
No | Risk |  | Status | Meter
1 | Payment Issues |  | Low | 10% | 5% | 0.5% | 94.5%
10%
10%
70%
2 | Lack of specializes skill required in the project |  | Medium | 10% | 15% | 0.5% | 84.5%
10%
10%
70%
3 | Team management risk |  | High | 10% | 25% | 0.5% | 74.5%
10%
10%
70%